## Relations
ID | Activity Name | Predecessor Activity | Rel | Lag
MOB1000 | Survey works
MOB1010 | Cleaning Leveling | Survey works | FS
MOB1020 | Erection Site Offices | Cleaning Leveling | FS
MOB1030 | Fixing the fence | Cleaning Leveling | FS
BSW1000 | Excavation | Survey works | FS
|  | Erection Site Offices | FS
|  | Excavation shop drawing | FS
BSW1010 | Dewatering | Excavation | SS | 4
|  | Water Proofing | FF
BSW1020 | Back Filling | Water Proofing Approval | FS
|  | Dewatering | FS
|  | Back Filling approval | FS
BSC1000 | Shuttiring PC Footing | Excavation | FS
|  | Excavation level approval | FS
BSC1010 | Pouring PC Footing | Concrete approval | FS
|  | Shuttering PC Footing | FS
BSC1020 | De shuttiring PC Footing | Pouring PC Footing | FS
BSC1030 | Shuttering RC footing | De shuttering PC Footing | FS
BSC1040 | Steel fixing RC footing | De shuttering PC Footing | FS
|  | Steel approval | FS
BSC1050 | Pouring RC footing | Shuttering RC footing | FS
|  | Steel fixing RC footing | FS
|  | Foundation RC pouring approval | FS
BSC1060 | De Shuttering RC footing | Pouring RC footing | FS | 1
BSC1070 | Shuttering Columns & Water tanks | De Shuttering RC footing | FS
BSC1080 | Steel Fixing Columns & Water tanks | De Shuttering RC footing | FS
BSC1090 | Pouring Columns & Water tanks | Shuttering Columns & Water tanks | FS
|  | Steel Fixing Columns & Water tanks | FS
|  | Basement Columns Pouring approval | FS
BSC1100 | De Shuttering Columns & Water tanks | Pouring Columns & Water tanks | FS | 7
BSC1110 | Water Proofing | Water Proofing material approval | FS
|  | De Shuttering Columns & Water tanks | FS
BSC1120 | Shuttering Slab & Stairs | Waterproofing | FS
BSC1130 | Steel Fixing Slab & Stairs | Waterproofing | FS
BSC1140 | Pouring slab & Stairs | Shuttering Slab & Stairs | FS
|  | Steel Fixing Slab & Stairs | FS
|  | Basement Slab Poouring approval | FS
BSC1150 | De Shuttering Slab & Stairs | Pouring Slab & Stairs | FS | 14
BSC1160 | Block Works | De Shuttering Slab & Stairs | FS