## Activities
WBS Name |  | Activity ID | Acitivity Name | Duration (d)
Engineering | Shop drawings | ESD1000 | Excavation Shop drawing | 5
|  | ESD1010 | Foundation Steel Shop drawing | 5
|  | ESD1020 | Columns Steel Shop drawing | 5
| Material Submittal & Approval | ESA1000 | Concrete approval | 3
|  | ESA1010 | Steel approval | 5
|  | ESA1020 | Water proof materials approval | 3
|  | ESA1030 | Excavation level approval | 2
|  | ESA1040 | Foundation RC pouring approval | 2
|  | ESA1050 | Basement Columns Pouring approval | 2
|  | ESA1060 | Waterproof approval | 2
|  | ESA1070 | Back Filling approval | 2
|  | ESA1080 | Basement Slab Pouring approval | 2
|  | ESA1090 | GF Columns Pouring approval | 2
|  | ESA1100 | GF Slab Pouring approval | 2
General Milestones |  | MIL1000 | Finishing Basement | 0
|  | MIL1010 | Finishing First Floor | 0
|  | MIL1020 | Finishing 4th Floor | 0
|  | MIL1030 | Finishing the project | 0
Mobilization |  | MOB1000 | Survey Works | 3
|  | MOB1010 | Cleaning and leveling | 3
|  | MOB1020 | Erection Site Offices | 3
|  | MOB1030 | Fixing Fence | 3
|  | MOB1040 | Demobilization | 2
Basement | Soil Works | BSW1000 | Execavation | 7
|  | BSW!1010 | Dewatering
|  | BSW1020 | Back Filling | 2
| Civil | BSC1000 | Shuttering PC Footing | 1
|  | BSC1010 | Pouring PC Footing | 1
|  | BSC1020 | De shuttering pc Footing | 1
|  | BSC1030 | Shuttering RC Footing | 2
|  | BSC1040 | Steel Fixing RC Footing | 2
|  | BSC1050 | Pouring RC Footing | 1
|  | BSC1060 | De Shuttering RC Footing | 1
|  | BSC1070 | Shuttering Columns & Water tanks | 5
|  | BSC1080 | Steel Fixing Colums & Water tanks | 4
|  | BSC1090 | Pouring Columns & Water tanks | 2
|  | BSC1100 | De Shuttering Columns & Water tanks | 2
|  | BSC1110 | Water Proofing | 4
|  | BSC1120 | Shuttering Slab & Stairs | 6
|  | BSC1130 | Steel Fixing Slab & Stairs | 5
|  | BSC1140 | Pouring Slab & Stairs | 1
|  | BSC1150 | De Shuttering Slab & Stairs | 2
|  | BSC1160 | Block works | 5
| Finishing | BSS1000 | Plaster | 8
|  | BSS1010 | Flooring | 5
|  | BSS1020 | Painting | 8
| Electrical | BSE1000 | Slab Electrical pipes | 2
|  | BSE1010 | Electrical First Fix | 3
|  | BSE1020 | Wiring & boxes | 3
|  | BSE1030 | Fixing lights & outlets | 3
| Mechanical | BSM1000 | Piping | 4
|  | BSM1010 | Fixitures | 4
Ground Floor | Civil | GFC1000 | Shuttering columns | 5
|  | GFC1010 | Steel Fixing columns | 4
|  | GFC1020 | Pouring concrete columns | 1
|  | GFC1030 | De Shuttering columns | 1
|  | GFC1040 | Shuttering Slab & Stairs | 6
|  | GFC1050 | Steel Fixing Slab & Stairs | 5
|  | GFC1060 | Pouring concrete Slab & Stairs | 1
|  | GFC1070 | De Shuttering Slab & Stairs | 2
|  | GFC1080 | Block works | 8
|  | GFC1090 | Toilets water proof | 6
| Finishing | GFF1000 | PLaster Preliminary | 2
|  | GFF1010 | Carpentry First Fix | 2
|  | GFF1020 | Fixiing Forged steel | 2
|  | GFF1030 | Plaster | 10
|  | GFF1040 | Gypsum Moulding | 6
|  | GFF1050 | Painting Preliminary | 7
|  | GFF1060 | Floor & Wall tiles | 8
|  | GFF1070 | Finishing carpentary | 6
|  | GFF1080 | Finishing painting | 6
| Electrical | GFE1000 | Slab Electrical pipes | 2
|  | GFE1010 | Electrical First Fix | 5
|  | GFE1020 | Electrical 2nd Fix | 5
|  | GFE1030 | Electrical Finishing | 3
| Mechanical | GFM1000 | Plumbing First Fix | 3
|  | GFM1010 | Supply & drain lines | 5
|  | GFM1020 | Finishing Plumbing | 3
First Floor | Civil | FFC1000 | Shuttering columns | 5
|  | FFC1010 | Steel Fixing columns | 4
|  | FFC1020 | Pouring concrete columns | 1
|  | FFC1030 | De Shuttering columns | 1
|  | FFC1040 | Shuttering Slab & Stairs | 6
|  | FFC1050 | Steel Fixing Slab & Stairs | 5
|  | FFC1060 | Pouring concrete Slab & Stairs | 1
|  | FFC1070 | De Shuttering Slab & Stairs | 2
|  | FFC1080 | Block works | 8
|  | FFC1090 | Toilets water proof | 6
| Finishing | FFF1000 | PLaster Preliminary | 2
|  | FFF1010 | Carpentry First Fix | 2
|  | FFF1020 | Fixiing Forged steel | 2
|  | FFF1030 | Plaster | 10
|  | FFF1040 | Gypsum Moulding | 6
|  | FFF1050 | Painting Preliminary | 7
|  | FFF1060 | Floor & Wall tiles | 8
|  | FFF1070 | Finishing carpentary | 6
|  | FFF1080 | Finishing painting | 6
| Electrical | FFE1000 | Slab Electrical pipes | 5
|  | FFE1010 | Electrical First Fix
|  | FFE1020 | Electrical 2nd Fix | 5
|  | FFE1030 | Electrical Finishing | 3
| Mechanical | FFM1000 | Plumbing First Fix | 3
|  | FFM1010 | Supply & drain lines | 5
|  | FFM1020 | Finishing Plumbing | 3
Roof & Staircase | Civil | RSC1000 | Parapet Wall | 2
|  | RSC1010 | Slope Screed | 2
|  | RSC1020 | Thermal Isolation | 2
|  | RSC1030 | Water Proofing | 6
|  | RSC1040 | Roof Tiles | 5
|  | RSC1050 | Block works | 2
| Finishing | RSF1000 | PLaster Preliminary | 2
|  | RSF1010 | Plaster | 4
|  | RSF1020 | Painting Preliminary | 4
|  | RSF1030 | Marble steps and skirting | 10
|  | RSF1040 | Fixing Handrail | 4
|  | RSF1050 | Finishing painting | 4
| Electrical | RSE1000 | Electrical Wiring | 4
|  | RSE1010 | Electrical works | 3
| Mechanical | RSM1000 | Roof Drains | 2
Outdoor Works | Facads | ODF1000 | Fixing Scaffolding | 2
|  | ODF1010 | Plaster Preliminary | 3
|  | ODF1020 | Plaster | 8
|  | ODF1030 | Painting Preliminary | 5
|  | ODF1040 | Fixing Stones and Marbles | 8
|  | ODF1050 | Removing Scaffolding | 1
| Fence & Gates | ODG1000 | Fence Columns | 7
|  | ODG1010 | Fence Walls | 10
|  | ODG1020 | Fixing gates Frames | 2
|  | ODG1030 | Electrical pipes and boxs | 4
|  | ODG1040 | Fence plaster | 5
|  | ODG1050 | Fixing Gates | 2
|  | ODG1060 | Finishing Painting | 3
|  | ODG1070 | Finishing Electrical | 2
| Landscaping | ODL1000 | Plumbing Pipes & taps | 3
|  | ODL1010 | Plumbing gullytraps & covers | 3
|  | ODL1020 | Cleaning and leveling walkway | 2
|  | ODL1030 | Planting | 3
| Walkways | ODW1000 | Screed For walkway | 2
|  | ODW1010 | Fixing walkway kerb-stone | 2
|  | ODW1020 | Fixing interlock tiles | 4
|  | ODW1030 | Finishing & Final Cleaning | 3